## Sheet1
Date | Employee ID | Employee Name | LG | Overall Work | What did you do yesterday? | What will you do today? | Did you faced any blockers?
2020-10-22 | 1807374 | Aman Abhishek | APY16 | 1. We got familiarised with the softwares. 2. Completed UI of home, sign in and sign up pages. |  | Got familiarised with flask | Which technology to work on(ie. flask, console based)
| 1781492 | Deep Ghodasara | APY16 |  |  | Worked on home page of website
| 1767687 | Jeetkumar Thummar | APY16 |  |  | Worked on UI sign-in/sign-up pages
| 1808659 | Simran Kathuria | APY16 |  |  | Got familiarised with flask
2020-10-23 | 1807374 | Aman Abhishek | APY16 | 1. We got familiarised with Github. 2. Completed working of sign-in/sign up pages with backend 3. Connected database with the project | Got familiarised with flask | Got familiarised with flask | -
| 1781492 | Deep Ghodasara | APY16 |  | Worked on home page of website | Got familiarised with Git
| 1767687 | Jeetkumar Thummar | APY16 |  | Worked on UI sign-in/sign-up pages | Worked on UI sign-in/sign-up pages
| 1808659 | Simran Kathuria | APY16 |  | Got familiarised with flask | Got familiarised with flask
2020-10-26 | 1807374 | Aman Abhishek | APY16 | 1. Almost completed working of customer management portal 2. Developed UI of admin, plans and status pages | Got familiarised with flask | Designed UI for plans page | How to collaborate with eachother and share the code
| 1781492 | Deep Ghodasara | APY16 |  | Got familiarised with Git | Worked on backend of admin portal
| 1767687 | Jeetkumar Thummar | APY16 |  | Worked on UI sign-in/sign-up pages | Worked on backend of profile page
| 1808659 | Simran Kathuria | APY16 |  | Got familiarised with flask | Designed UI for current status
2020-10-27 | 1807374 | Aman Abhishek | APY16 | 1. Completed Customer Management portal 2. Completed Tariff Plan Management Portal 3. Integrated both portal in one system and tested the working | Designed UI for status page | Designed UI for status page | Integration of the all codes
| 1781492 | Deep Ghodasara | APY16 |  | Worked on frontend of plan portal | Worked on frontend of plan portal
| 1767687 | Jeetkumar Thummar | APY16 |  | Worked on backend of plan portal | Worked on backend of plan portal
| 1808659 | Simran Kathuria | APY16 |  | Designed UI for plan page | Designed UI for plan page