## Sheet2
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
Customer Management Portal and Tariff Plan Management Portal | As a…. | Task 1 | Aman | Design the UI for the Customer Portal | 36 | 27 | 18 | 12 | 9 |  |  | closed
|  | Task 2 | Deep | Design backend code of Customer Portal | 36 | 27 | 18 | 10 | 4 |  |  | closed
|  | Task 3 | Jeet | Design backend code of Tariff Management Portal | 36 | 27 | 18 | 13 | 5 |  |  | closed
|  | Task 4 | Simran | Design the UI for the Tariff Management Portal | 36 | 27 | 18 | 9 | 6 |  |  | closed
--

## Sheet1
Days | Actual Effort Remaining | Ideal Effort Remaining
0 | 144 | 144
1 | 112 | 108
2 | 72 | 72
3 | 40 | 36
4 | 20 | 0
5 | 0